## Sheet1
Retrospective - Gold Team - Hands Up America / Tax Project
2020-03-27
Keep doing
Standups at the start, staying coordinated / on task
Fluid about what was needed, ongoingly
MVP focus…. Good to stay on track
Structured time well in blocks
Everyone contributed well
Started with high level timeline / goals
Define narrative from the beginning
Great presentation
Stop doing:
Squirrels! Tighten up on the wild goose chases / exploration.
More emphasis on getting questions completed, everyone on team.
Do more things wrong.
Start doing
Ask for help / clarification more often, sooner.
Get MVP done sooner
Way to get to know each other a bit better…
Have a conversation with each person in the group individually at beginning of group - one on one.
What do you want to learn in this project; what can you do well/quickly.
Group lunches once back "in person" or via separate zoom room.